## Sheet1
ID | Start time | Completion time | Email | Name | Date of entry | Stage | What happened? | What went well? | What didn't go so well? | What lessons were learned? | What could be done better? | Next steps | How significant was this event for the project? | How significant was this event for me personally?
1 | 2022-02-04 15:49 | 2022-02-04 15:54 | anonymous |  | 2019-04-19 | Pilot | I sent a one-pager containing my data linkage interest to the ABS. | They were open to entertain my proposal. | They had no established process for dealing with it. May take a while for them to answer. | It's better to get in while rules aren't firmly established. | I could have pressed them for a more definite time table. | Follow-up in a week or two. | 4 | 2
2 | 2022-02-04 15:54 | 2022-02-04 16:00 | anonymous |  | 2017-08-25 | Pilot | A letter from DPC to RTWSA to link data to BLADE with proposed project plan is submitted for my CE's approval | I established contact and agreement with RTWSA at the officer level before elevating it to the CEs. | The time it took to get agreement from RTWSA managers. Needed to brief CE from zero knowledge. Very tedious. | Knowing that my CE was detail oriented allowed me to know at what level to pitch the project. | I could have worked with my CE's correspondence team more closely. | Chase this up with RTWSA | 4 | 2
3 | 2022-02-04 16:00 | 2022-02-04 16:05 | anonymous |  | 2017-08-31 | Pilot | A formal data integration project proposal application is initiated | The ABS is on our side and very receptive, it seems from what I heard from their embedded officer. | Had to initiate this to get data through Census Act rather than through the Office for Data Analytics as originally planned. | When obstacles get in the way, find another way around. | Establishing a more cooperative and collaborative culture that supports data sharing. | Get feedback from ABS governance committee that will decide on our application | 5 | 3
4 | 2022-02-07 10:46 | 2022-02-07 10:51 | anonymous |  | 2017-09-05 | Pilot | ODA data sharing agreement request application is initiated | The office finally modified its template to allow for multilateral data sharing agreements | That it took so long, because they were swamped with other work, and there was no precedent for this. | Being patient and persistent without being annoying (delicate balance). | Have more constant communication and scheduled meetings to put pressure on them to finish things. | Finalise application and follow through | 5 | 4
5 | 2022-02-07 10:51 | 2022-02-07 10:58 | anonymous |  | 2018-02-23 | Pilot | SA BLADE steering group convened. Pilot kicks off! | Engagement and goodwill from all stakeholders. Our chair steered meeting well. Got members to commit. | A bit of argy-bargy with regard to Commonwealth stakeholders over access to data. | Choosing our chair was an inspired decision. High level champion of data driven policy making being a scientist. | We could have managed stakeholders at the Commonwealth level better through ABS partnerships officer. | Get the data in. Get the team going on replication study/first bit of analysis while waiting for data integration. | 5 | 5
6 | 2022-02-07 11:04 | 2022-02-07 11:10 | anonymous |  | 2018-06-20 | Pilot | Replication of Commonwealth BLADE paper presented | The work was done with advice from DISER researcher. | Dependency on one single analyst with technical skills is a risk | Taking advantage of Cth partner's interest as it aligns with their KPIs helps ease us into the project | Screening the analyst pool better. | Prune the analyst pool. Get other analysts with technical skills. | 4 | 4
7 | 2022-02-07 11:12 | 2022-02-07 11:24 | anonymous |  | 2018-09-18 | Pilot | Completion of SA data integration into BLADE confirmed. Proposed inter-agency research topics approved | Match rate quite high. Topics nominated by each agency keeps them engaged. | Only one year of RTWSA data linked. Decided while I was away with no consultation by ABS partnerships manager. Will reduce usefulness of data. | Never assume that partners are on your side. It's important to cultivate trust on an ongoing basis. | More convincing of my minder that we are good faith operators and that they have as much at stake here as we do. | Implement the feasible research topics. | 4 | 4
8 | 2022-02-07 11:24 | 2022-02-07 11:28 | anonymous |  | 2018-12-06 | Pilot | Training of additional SA BLADE analysts completed | Qualified analysts and interested discussants were signed on. | Not enough analysts still. Too many discussants/chefs supervising the cooking. | State government is a limited pool from which to recruit analysts. | Bring in other qualified analysts by expanding the recruitment pool or catchment area. | Work with new analysts for the implementation of other research projects. | 4 | 3
9 | 2022-02-07 11:29 | 2022-02-07 11:40 | anonymous |  | 2018-12-12 | Pilot | First diagnostic study of firms using RTWSA in BLADE | Demonstrable usefulness of RTWSA data, even for just one year, in terms of disaggregating activity of complex firms. | Not knowing where to from here, as we only got one year's worth of data integrated | Having good analysts really helps. Junior officers, recent graduates are the best source within SA government | Improving external communication of these results | Move on to other research projects on the agenda | 5 | 4
10 | 2022-02-07 13:41 | 2022-02-07 13:47 | anonymous |  | 2019-04-04 | Pilot | Payroll tax study - a natural experiment - presented | Report was well received within sponsoring agency, demonstrated capacity | Results not very conclusive | Sometimes the way the policy research is framed needs to be changed to be addressed by the data | Have a better alignment with state government priorities to gain greater relevance | Proceed with suggested extensions of the study | 3 | 3
11 | 2022-02-07 13:47 | 2022-02-07 14:17 | anonymous |  | 2019-04-05 | Pilot | Steering group approves mode of collaborating with universities | Commercial division's and procurement team's advice and assistance from legal intern proved crucial | The time it took to get the MOU and draft contracts prepared since collaborations aren't the norm | Procedures on doing this take up a long time. | The portal - wish we had not invested so much time on an untested platform | Get expression of interest out and assess proposals | 5 | 3
12 | 2022-02-07 14:17 | 2022-02-07 14:19 | anonymous |  | 2019-06-18 | Pilot | 3-yr MOU with Adelaide University commences, first service agreement signed for advisors | Parties were flexible and easily arrived at an agreement. | Legalistic approach by other unis led to a breakdown of potential collaborations | Work with parties that meet you half-way. | Better communicate inadequacies of approach taken by other unis. | Work with partners to get work done! | 5 | 4
13 | 2022-02-07 14:20 | 2022-02-07 14:24 | anonymous |  | 2019-09-27 | SA BLADE 2.0 | Senior Management Council of CEs endorse SABRE/BLADE | Presentation at SMC went well. My CE backed me and I got a few suggestions. | I could have been more receptive to ideas pitched by one CE | Getting senior level buy-in helps to legitimise the project to get SABRE off the line, Going there early was the key and keeping it "high level" | Backgrounding CEs through officer network more. This will be needed in the future. | Prepare for SABRE agreement to be signed. | 5 | 4
14 | 2022-02-07 16:16 | 2022-02-07 16:22 | anonymous |  | 2019-10-17 | Pilot | Final work on three policy analysis questions presented | Reports were well received | Many senior officers weren't able to attend - too busy with other things now. | The collaboration with the university was the most productive piece. | The DPC data scientist was not an economist. Selecting someone with the right skill set to reduce learning curve is needed next time. | Draft MOU with ABS for second stage, define next round of questions to work on. | 4 | 3
15 | 2022-02-07 16:37 | 2022-02-07 16:40 | anonymous |  | 2020-01-28 | SA BLADE 2.0 | SABRE data sharing agreement signed by 10 SAG agencies | All agencies signed up in the end without too much hassle. | No support or presence of ODA. | Having done all the legwork at mid-to-senior level ensured cooperation from all concerned. | More support from ODA | Get the data and set up SABRE working groups to deliver integrated data into ABS data lab | 5 | 4
16 | 2022-02-07 16:46 | 2022-02-07 16:50 | anonymous |  | 2020-02-13 | Pilot | SA BLADE presentation at BLADE Expo at UNSW Sydney. First time to address an external audience. Good publicity. | Presentation was well received by inter-state government colleagues | Finding the venue, flights, bookings. | Be more organised. | I could have done a better job at creating background notes for the data presented | Doing the work that we originally planned to do around the source of the state's growth in FTEs | 3 | 5
17 | 2022-02-07 16:53 | 2022-02-07 16:58 | anonymous |  | 2019-07-10 | Pilot | Steering group meeting with new BLADE integration director from ABS | Got to meet new official - established good working relationship | Meeting was poorly attended, stakeholder engagement low, nothing much to present, losing momentum | Need to show progress on the analytical front | Getting stronger support from the ABS to speed up processes, new director may be able to help | Work faster to ensure deliverables are met for the next meeting. | 2 | 1
18 | 2022-02-07 16:58 | 2022-02-07 17:03 | anonymous |  | 2019-06-27 |  | Initial scoping of work on high growth firms with stakeholders and university advisers | Stakeholders were on board, cooperative, funding and analyst provided, advisers were quite effective | Payments for advisers, bureaucracy of getting payments through | Having stakeholders that are on your side and willing to work with you is key | Better handling of administrative matters between agencies | Implement work plan | 3 | 3
19 | 2022-02-07 17:06 | 2022-02-07 17:09 | anonymous |  |  | Pilot | Tri-state meeting on innovation metrics and analysis | Hosting by Lot Fourteen was an inspired choice. Great collaboration with other states, commitment to keep meeting | Technical/IT issues. DDG from Advance Qld backing out, had to step in. | Presenting SA BLADE at Expo and putting yourself out there results in making connections that lead to new things. | Preparing and testing technology before hand | Keep engaging with interstate stakeholders. | 3 | 3
20 | 2022-02-07 17:11 | 2022-02-07 17:13 | anonymous |  | 2019-02-24 |  | Collaboration with CSIRO begins - to work on mining question | Their openness. Having worked with DEM on other projects allowed ease of doing business with each other. | Still a bit unclear on the legal/financial requirements for their engagement | Having experts on board to guide the work is important, especially as our data scientist is not an economist |  | Keep talking, sending more material to them. Arranging next meet up. | 3 | 2
21 | 2022-02-07 17:15 | 2022-02-07 17:18 | anonymous |  | 2019-08-06 | Pilot | Data lab breach incident discussed | We avoided the worst case scenario. A new analyst stepped up to replace suspended one. | This will hamper the work and set us back, at a time we can least afford. | Taking your medicine showed the other side that we were conscientious users, and good faith operators. | Stronger protocols and supervision of analysts to ensure this doesn't happen again. | Work with strategic partnerships manager to get through this. | 1 | 1
22 | 2022-02-08 10:56 | 2022-02-08 11:03 | anonymous |  | 2021-04-01 | SA BLADE 2.0 | Co-design workshops for SA BLADE 2.0 conducted | The virtual workshops were well attended by state government and university people who were all interested and willing to collaborate. | Some people had difficulty logging on to the meeting. | It's possible to forge partnerships and open collaboration between the state and research communities. | The balance across topics. More people could have been invited to have a better discussion in some breakout rooms. | Prepare the scope of work for SA BLADE 2.0. | 4 | 5
23 | 2022-02-08 11:03 | 2022-02-08 11:08 | anonymous |  | 2021-04-23 | SA BLADE 2.0 | SABRE Reference Group (RG) approves terms of reference | The excitement and engagement of the members to see SABRE take flight was evident at the meeting. | The data quality report from ODA was not available, only a verbal update. | Having honest partners on board is vital for any project of this sort. | Pressing ODA to be serious about supplying reports. | Organise the technical working group and prepare recommendations to the reference group next time. | 3 | 3
24 | 2022-02-08 11:09 | 2022-02-08 11:15 | anonymous |  | 2020-06-10 | Pilot | Pilot evaluation study noted by SG; Pilot concluded | The evaluation findings were well received by the steering group members. The ABS committed to the next round. | Resourcing of the second round is still uncertain. | The innovation is feasible and useful to state government. It just needs to be more aligned to the priorities of the current government. | The second round needs to be aligned with the government's policy agenda to show relevance and gain funding. | Prepare for second round implementation. | 4 | 4
25 | 2022-02-08 14:16 | 2022-02-08 14:21 | anonymous |  | 2020-06-10 | SA BLADE 2.0 | Scope for SA BLADE 2.0 approved by Steering group | The scope was approved without any major concerns. It's more aligned with SA government priorities this time. | Not as much engagement from members at the meeting. Too caught up with other priorities. | The collaborative approach with the university is worth pursuing. | Deeper engagement with university partners. | Work to implement the scope. Organise community of practice. | 4 | 3
26 | 2022-02-08 14:21 | 2022-02-08 14:26 | anonymous |  | 2020-09-30 | SA BLADE 2.0 | Community of Practice session 1 | Presentations were well received. Potential offshoots of analysis were identified. | Not enough time to discuss implications of ARC linkage grant proposal to SA BLADE project. | It is possible to use BLADE to do regional and growth profiles for impact assessment that is useful for stimulus and other forms of assistance. | Better time management at meetings. Some presenters take too long to get to the point. | Schedule presentations on different topics next time. Carry out extension of completed projects. | 3 | 3
27 | 2022-02-08 14:43 | 2022-02-08 14:47 | anonymous |  | 2020-10-20 | SA BLADE 2.0 | Community of Practice session 2 | The deep dive into Growth State estimates was useful. | A bit long-winded in some parts of the presentation. | It's good to collaborate across SA government | Being kept in the loop with the analytical work. | Follow-up the data integration with ABS | 3 | 2
28 | 2022-02-08 15:09 | 2022-02-08 15:13 | anonymous |  | 2020-04-03 | SA BLADE 2.0 | Discussions with ODA regarding the use of SABRE | Both sides got to air their views | Parts of discussion got heated over governance and scope | The creation of SABRE created a lot of complexity and sources of potential organisational friction. | Focusing on the common agenda. Establishing rules of engagement early on. | Ensure governance of SABRE is maintained despite alternative agendas. | 1 | 1
29 | 2022-02-08 15:13 | 2022-02-08 15:24 | anonymous |  | 2020-12-01 | SA BLADE 2.0 | Community of practice session 3 | Met with AusTrade to discuss their data integration of customer relationship management database. Good exchange. | Not sure how to translate it to our project. This stretches the concept of SABRE a bit. | Need to keep eyes open for other opportunities like this one. Need to keep engaging with federal and state colleagues. | More background material needs to be shared prior to the meeting. | Set up a follow-up meeting to get some answers to lingering questions. | 2 | 2
30 | 2022-02-08 15:43 | 2022-02-08 15:46 | anonymous |  | 2019-10-17 | SA BLADE 2.0 | Steering group endorsed signing of MOU with ABS for linking SABRE into BLADE thru ODA | Framework for mutual cooperation and benefit reached. | Having to do all the legwork for ODA in getting MOU drafted and sent through the system | Ensuring that major stakeholders are satisfied requires personal sacrifice sometimes. | Having more support! | Get the MOU finalised and signed. | 2 | 1
31 | 2022-02-08 15:46 | 2022-02-08 15:52 | anonymous |  | 2020-02-14 | SA BLADE 2.0 | Meeting in Brisbane to plan/organise ARC/Team Australia | It was a very productive meeting. Parties agreed to forge ahead. | Some internal friction or detachment between some members within partner organisation. | Re-purposing the meeting to focus of our plans cemented a deep bond of friendship and partnership. | Organising the meeting to avoid conflicts with some of the hosting parties. | Stay in touch. Follow through on the plans. | 3 | 4
32 | 2022-02-08 15:55 | 2022-02-08 15:58 | anonymous |  | 2020-09-23 | SA BLADE 2.0 | Team Australia pitch made | Support of two states plus Commonwealth achieved. Meeting was well-attended despite narrow focus. | Some attendees backed out or dropped out of the call. Technical issues ensued during the call. | Having early preparation of devices worked. Having good back plans helped. | Making contact with other parties to confirm their attendance. Personal touch. | Finalise interested parties and get their commitments. | 3 | 4
33 | 2022-02-08 15:59 | 2022-02-08 16:02 | anonymous |  | 2020-09-25 | SA BLADE 2.0 | First MADIP study on interstate migration launched | Clarified role of partners, analysts and firmed up commitment from sponsor | Some academics couldn't commit. Became a deterrent to working with them. | Having the discussion and clarification of roles early saves time down the track. | Gotten a better handle on what parties were willing to commit to. | Undertake analysis and organise follow-up meeting. | 4 | 3
34 | 2022-02-08 16:46 | 2022-02-08 16:48 | anonymous |  | 2020-10-27 | SA BLADE 2.0 | SABRE submitted and suitability confirmed by ABS team | ABS was quick in studying data and getting back to us for any problems to be remedied | The time it took ODA to get the data ready | SABRE adds an extra layer of processing and time that needs to be reduced and planned for. | Getting the data in sooner. Having the necessary people in place. | Coordinate with ABS on the data integration | 3 | 3
35 | 2022-02-08 16:50 | 2022-02-08 16:53 | anonymous |  | 2020-12-03 | SA BLADE 2.0 | Collaboration with MIT Living Lab analyst assessed and approved. | The expansion of collaborative partners to MIT Living Lab. | Initial discussions got off on the wrong foot, but immediately rectified. | Being open and flexible to work with different types of partners. | Being more customer friendly. Not being resistant to novel ideas. | Work with partner to get their needs met. | 4 | 3
36 | 2022-02-08 16:53 | 2022-02-08 16:56 | anonymous |  | 2020-12-22 | SA BLADE 2.0 | Problems with program and sector data reported and dealt with | An immediate solution was found for the sector data. | Program data could not be rescued. | Giving clear instructions to ODA. Clarifying assumptions. Being in close lock step. | Better integration and documentation. | Follow-up data in the new year. | 1 | 1
37 | 2022-02-11 14:22 | 2022-02-11 14:25 | anonymous |  | 2021-02-18 | SA BLADE 2.0 | Recruitment/hiring of HDR students commences | Recruits are enthusiastic about working with the data. It's a selling point. Plus they get paid work while doing their research. Win-win. | That it took so long to speak to them. Identifying recruits. I had to get involved. | Engage early. Reach out, and don't be afraid to actively recruit. | The advertising and promotion of openings. | Arrange for their training and hiring through agency. | 4 | 4
38 | 2022-02-11 14:25 | 2022-02-11 14:39 | anonymous |  | 2021-02-23 | SA BLADE 2.0 | Community of practice session 4 | Discussions with project proponents were productive. Got to discuss startup report and Magnet State studies. | Very dependent on one analyst for both studies. Need HDR students to fill the gaps. | MADIP is a viable product for state government analysis. Our startup definition is taking shape. | Having more analysts to help out. | Push for the completion of these bits of work. Continue working with stakeholders to meet and manage expectations. | 3 | 3
39 | 2022-02-11 14:39 | 2022-02-11 14:41 | anonymous |  | 2021-03-01 | SA BLADE 3.0 | Scoping of innovation district frame with stakeholders | Good will from stakeholders all around. Proposals are well received. Interest and engagement is good. | Structure is still needed around how to manage this group. | Need to evolve the governance of SA BLADE to include working groups like this, which will be vital in the future. | Deeper engagement and more thorough communication with each stakeholder. | Seek advice on how to manage this. | 4 | 3
40 | 2022-02-11 14:42 | 2022-02-11 14:45 | anonymous |  | 2021-03-04 | SA BLADE 3.0 | Meet with advisor from Project Management Office | I received positive advice and reinforcement. I was told, "there is no reason why we shouldn't be doing this, other than lack of funds. You are transforming the way we do policy. This is apparent to anyone who understands." | I was a little late. | That others appreciate the value of what we are doing. We need to forge ahead no matter what. | Organise the stakeholders as a working group with our Chief Scientist as the chair. | Seek the Chief Scientist's endorsement for the governance arrangement and to co-host as chair when the workshops are run. | 4 | 4
41 | 2022-02-11 15:02 | 2022-02-11 15:31 | anonymous |  | 2021-03-19 | SA BLADE 2.0 | Growth State sectoral data presented to stakeholder group | Presentation was well attended by all. Positive feedback received from the group. Support expressed for ongoing work. | A lack of face-to-face contact (most cameras were off) made it a little impersonal. | The SA BLADE model is accepted and works well. It can be replicated in the next round and improved on. | The program data was rendered useless by the way it was joined up by the ODA/ABS. | Need to prepare for the third round of integration. Keep the stakeholders informed. | 5 | 4
42 | 2022-02-14 11:45 | 2022-02-14 12:12 | anonymous |  | 2021-04-09 | SA BLADE 3.0 | Kickoff, skirmish between ODA and ABS | Better understanding and agreement with the ABS on a range of issues | ODA could not attend. Other commitments ie response to Covid preventing them to join. | Soldier on despite difficulties. | Better engagement from ODA | Schedule follow-up meetings to discuss and socialise solutions and ideas. | 3 | 2
43 | 2022-02-14 12:12 | 2022-02-14 12:24 | anonymous |  |  | SA BLADE 2.0 | Community of practice/Policy Analyst Group meet | A deep dive into the Growth state sector estimation techniques was discussed and received well. New recruits for analyst group identified. | Some agencies were less interested as their sectors were well covered by existing conventions. | The importance of using SABRE and BLADE in tandem with RISE to provide better estimates. A stronger foundation for future work. | Better documentation of the approach. | Work with stakeholders for the next update. | 3 | 4
44 | 2022-02-14 12:24 | 2022-02-14 12:28 | anonymous |  | 2021-05-14 | SA BLADE 3.0 | Innovation district multi-agency data frame workshops kick-off | Good, healthy discussion. Interest and engaged participation from those in attendance. | Technology issues with teleconferencing equipment. | Humility and accepting unfortunate things with good humor. | Getting someone on board to help with administrative and technical issues. | Continue workshops and get support and agreement on the plan for incorporating district data in SA BLADE. | 4 | 4
45 | 2022-02-18 10:16 | 2022-02-18 12:12 | anonymous |  | 2021-05-28 | SA BLADE 2.0 | SME business study reference group kicks off | Good engagement from all major stakeholders was observed. A solid understanding of their requirements was arrived at. | Some grey areas still need to be sorted. The wait time for analysts to have access could delay the project. | Having ongoing communication with academics allowed us to capitalise when the opportunity to do work presented itself. | Circling back to stakeholders to ensure their worries and concerns are dealt with. | Meet regularly with the team. Monitor progress. | 5 | 4
46 | 2022-02-18 12:15 | 2022-02-18 12:21 | anonymous |  | 2021-07-13 | SA BLADE 2.0 | Community of practice/Policy Analyst Group meet |  | An interesting discussion on the startups and Atlas of Opportunity work took place. Valuable feedback received on how to improve them. | Having academics involved with the community of practice adds so much value to the SA government work. | Having more people in the datalab checking the work before it is presented. | Arranging a speedy turnover of work since one of the presenters is leaving. | 4 | 3
47 | 2022-03-14 12:41 | 2022-03-14 13:13 | anonymous |  | 2021-08-13 | SA BLADE 2.0 | Completion of SME paper | The goals of the research project were met, including the analytical portion delivered from BLADE. This included work that had never been done before. | The timing of the analysis. The BLADE access to new users took so long to arrange. It delayed the delivery date. | The collaboration with university is yielding results. It augments and addresses the skills gap within state government. | Faster referrals from the university. Need to find a ready pool of analysts for future work. | Expand the search for talent. | 4 | 4
48 | 2022-03-14 13:13 | 2022-03-14 13:23 | anonymous |  | 2021-10-04 | SA BLADE 2.0 | Presentation of MA students and SME work to stakeholder group | The presentations were well received by analysts and policy area managers. Insights that were never before developed for the state were produced. | The time wasn't sufficient to tease out in detail the analyses, only 20 minutes per presenter. | Aligning the theses of students with policy research agenda is possible and cost-effective. | Closer linkage and collaboration with policy area managers could be improved. | Encourage more collaborations in the future. | 5 | 5
49 | 2022-03-14 13:31 | 2022-03-14 13:37 | anonymous |  | 2021-10-13 | SA BLADE 2.0 | Deloitte presentation of report to Creative Industry group | The industry representatives latched on to the baseline estimates. They were very engaged and positive about its uses. | Lots of misunderstandings still about the nature of the data, what can and can't be done using it. | The wider audience is willing and interested to participate. Their education needs to be deepened and expanded. | A deeper understanding and broader dissemination of the data and what it represents is needed. | Continue talking to the policy area managers to expand usage and allow broader consultation and communication. | 4 | 5
50 | 2022-03-14 13:42 | 2022-03-14 14:03 | anonymous |  | 2021-10-13 | SA BLADE 3.0 | CE council approves funding contributions of agencies for next 3 years/rounds | Additional funding came from an unexpected source. Commitments that looked doubtful were locked in. | Some vagueness in the resulting minute required us to do further liaison with agencies to confirm specific amounts of contribution. | When making recommendations through minutes to governing bodies, state clearly what you are asking them to approve. | Be clearer in stating recommendations in minute to governing bodies to remove doubt as to actual commitments. | Work with finance to lock in the commitments through interagency budgets and get confirmation from treasury. | 5 | 5
51 | 2022-03-14 14:25 | 2022-03-14 14:30 | anonymous |  | 2021-10-28 | SA BLADE 3.0 | SABRE 2.0 delivered to ABS for SA BLADE 3.0 | The data merge did not take as long with SABRE 2.0 as it did in its first round. | Delivery was still delayed due to questions over a field that ODA wouldn't accept at first because it wanted to perform its own analysis. | Use the governance groups like the working group in DPC in charge of Growth State to deal with ODA's concerns. | Seeking clarity and guidance from above to sort out sectoral mapping. | Work with ABS to get SA BLADE 3.0 data out. | 4 | 3
52 | 2022-03-14 14:30 | 2022-03-14 14:33 | anonymous |  | 2021-11-02 | SA BLADE 3.0 | ODA thru Economic Data Asset Committee takes carriage over SABRE | Close coordination between committee members prevented SA BLADE from being taken over. | A lack of clarity over governance resulted. Is ODA taking carriage over the creation of a SABRE platform only or the entire project? | Having stakeholders on your side is the best protection against organisational politics. | Greater transparency from parties to understand more clearly what their intentions are. | Work with ODA to clarify the handover of responsibilities and roles moving forward. | 3 | 2
53 | 2022-03-14 14:35 | 2022-03-14 14:38 | anonymous |  | 2021-11-30 | SA BLADE 3.0 | National pilot for Startup Data commissioned | The national working group recognised SA BLADE as a pioneer in this field and was given the green light to commence a national pilot on its behalf. | A bit of confusion over which model to use, SA or Queensland's as other parties got involved. | The collaboration with other states and territories pays off in the end. Goodwill and support was generated. | Better coordination and liaison with the national agencies to understand what their requirements are. | Engage with partners to prepare the team to undertake the work and get guidance from national agencies. | 5 | 5
54 | 2022-03-14 14:59 | 2022-03-14 15:02 | anonymous |  | 2021-12-20 | SA BLADE 3.0 | SA BLADE 3.0 loaded on to data lab – work commences | The ABS pulled through, allowing us to meet our deadlines for updating the Growth State sectors | The delays caused by the ODA/SABRE linkage. | Giving ODA carriage and responsibility for SABRE will elicit greater willingness and cooperation on their part moving forward. | Having a quicker turnover which will be facilitated by ODA gaining greater familiarity with data sets. | Work with analysts to produce Growth State updates, test program and innovation districts data. | 4 | 3
55 | 2022-03-14 15:03 | 2022-03-14 15:06 | anonymous |  | 2022-01-18 | SA BLADE 3.0 | National pilot using SA BLADE 3.0 commences | Initial scoping meeting conducted with all parties on board. | Inexperienced project officer assigned to oversee us, left many aspects lacking, such as clear definition of project scope and direction moving forward. | Having clear guidelines and cooperation is needed from the start. Don't take governance for granted. | Be prepared with materials before the meeting to present your case. | Work with stakeholders to clarify scope and work on a project plan to present at next meeting. | 3 | 3
56 | 2022-03-14 15:06 | 2022-03-14 15:10 | anonymous |  | 2022-02-17 | SA BLADE 3.0 | Program data summary tables presented to stakeholders | The program data presentation was well received. A lot of engagement and support was given to the team. | Matching rate and accuracy of data could be improved. | Data quality from the start is key. Designing programs as evaluation ready would deal with most data issues. | Better collection of data is needed, especially around approvals of grants and payments. | Seek authorisation to perform stage two analyses from governance bodies. | 4 | 5
57 | 2022-04-11 09:42 | 2022-04-11 10:51 | anonymous |  | 2022-04-01 | SA BLADE 3.0 | Innovation district summary statistics delivered | The matching rate was high and the data linked was used in providing initial measurement of their economic footprints.t. | Had to switch analysts mid-stream as the original one went to another department | The limits of the data - it challenge some underlying assumptions that we held about the subjects | Improve classification of firms during the data collection stage. | Feed back the results to stakeholders. Bring them along. | 4 | 4